## Slide 1
Northstar Programme Portfolio Update
Synthetic fixture – all names and details are fictional
Reporting date: 15 July 2026
Development challenge fixture
Fictional data created for portfolio testing; this is not a real record.

## Slide 2
Executive summary
Synthetic fixture – all names and details are fictional
Programme status Green
Programme owner Emma Clarke
Approved budget GBP 1.35 million
Target launch 15 December 2026
Reporting date 15 July 2026

## Slide 3
Workstream status table
Synthetic fixture – all names and details are fictional
Workstream | Owner | Status | Target date
Data Platform | Noah Bennett | Amber | 30 September 2026
Service Portal | Chloe Hart | Green | 15 November 2026
Training and Adoption | Aisha Cole | Green | 1 December 2026

## Slide 4
Delivery workflow
Synthetic fixture – all names and details are fictional
Pilot workflow
Ingest
Validate
Enrich
Publish
Human review between Enrich and Publish

## Slide 5
Risk register
Synthetic fixture – all names and details are fictional
Risk ID | Risk | Rating | Owner | Response
R-01 | Vendor integration delay | Medium | Noah Bennett | Weekly integration checkpoint
R-02 | Source-data quality | High | Chloe Hart | Validation rules and exception queue
R-03 | Training capacity | Low | Aisha Cole | Train-the-trainer plan

## Slide 6
Approved decisions and change log
Synthetic fixture – all names and details are fictional
Change | Previous value | Current value | Approval or effective date
Budget | GBP 1.20 million | GBP 1.35 million | Approved 10 July 2026
Target launch | 30 November 2026 | 15 December 2026 | Approved 12 July 2026
Programme owner | Alex Morgan | Emma Clarke | Effective 14 July 2026

## Slide 7
Superseded snapshot – 30 June 2026
Synthetic fixture – all names and details are fictional
SUPERSEDED – do not use as the current programme position
Programme status Amber
Programme owner Alex Morgan
Budget GBP 1.20 million
Target launch 30 November 2026